## Project Planner
ML Spring 2025 Plan
Select a period to highlight at right. A legend describing the charting follows. |  |  |  |  | Period Highlight: | 3 |  |  | Plan Duration | [5 empty] | Actual Start |  |  |  |  | % Complete |  |  |  |  | Actual (beyond plan) | [7 empty] | % Complete (beyond plan)
ACTIVITY | PLAN START | PLAN DURATION | ACTUAL START | ACTUAL DURATION | PERCENT COMPLETE | PERIODS
[6 empty] | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52 | 53 | 54 | 55 | 56 | 57 | 58 | 59 | 60
Dataset Collection & Review: HMDA, Loan Approval Prediction, Lending Club | 1 | 2 | 1 | 2 | 100%
Proposal Preparation | 2 | 2 | 2 | 2 | 100%
Data Cleaning & Preprocessing: Fair Encoding, Causal Inference, SMOTE, Normalization | 4 | 2 | 4 | 2 | 0%
Feature Engineering: Mutual Information-Based Selection | 4 | 2 | 4 | 2 | 0%
Model 1 (Supervised - Logistic Regression): Implementation & Evaluation | 5 | 3 | 5 | 3 | 0%
Model 2 (Unsupervised - SOM + Classifier): Implementation & Evaluation | 5 | 3 | 5 | 3 | 0%
Fairness Adjustment: Adversarial Training to Reduce Bias | 7 | 3 | 7 | 3 | 0%
Initial Evaluation: Confusion Matrix, Precision, Recall, Accuracy | 6 | 2 | 6 | 2 | 0%
Midterm Report Submission: GitHub Updates + Contribution Table | 7 | 1 | 7 | 1 | 0%
Model 3 (Supervised - SGD): Implementation & Evaluation | 8 | 2 | 8 | 2 | 0%
Advanced Model Tuning: Hyperparameter Optimization for SGD and SOM models | 9 | 2 | 9 | 2 | 0%
Fairness Metrics Evaluation: Assess Demographic Disparities Using Appropriate Fairness Metrics | 9 | 2 | 9 | 2 | 0%
Cross-Dataset Validation | 9 | 2 | 9 | 2 | 0%
Model Comparison: Trade-Off Analysis on Accuracy, Fairness, and Interpretability | 10 | 2 | 10 | 2 | 0%
Ethical Review: Focus on Fairness, Bias Correction, and Socioeconomic Impact | 10 | 2 | 10 | 2 | 0%
Final Report Completion: Comprehensive Model Analysis + Visualizations | 11 | 2 | 11 | 2 | 0%
Final Presentation Preparation: Visualizations + Key Insights | 11 | 2 | 11 | 2 | 0%
Final Presentation & Q&A: 9-Minute Presentation + 3-Minute Q&A | 12 | 1 | 12 | 1 | 0%
GitHub Repository Final Updates: Code, Visualizations, Updated README.md | 12 | 1 | 12 | 1 | 0%
| 0 | 0 | 0 | 0 | 0%
| 0 | 0 | 0 | 0 | 0%
| 0 | 0 | 0 | 0 | 0%
| 0 | 0 | 0 | 0 | 0%
| 0 | 0 | 0 | 0 | 0%
| 0 | 0 | 0 | 0 | 0%
| 0 | 0 | 0 | 0 | 0%